## ODB@AWS
Date | Issue | Status | Priority | Oracle Tracking Request | Type | Product | Contact | Description | Fidelity Comments | Oracle Progress/Comments
2025-05-02 | Oracle VM Provisioning via AWS | Not Resolved | Medium |  | Enhancement |  |  | Oracle VM Provisioning via AWS: When provisioning Oracle VMs through the AWS console, hardware problems or degradation on the OCI Side doesn’t appear on the AWS, preventing us from provisioning VMs on degraded hardware. Unfortunately, we only become aware of these issues when the VM provisioning process runs for 14 hours or longer. It would be beneficial to detect these failures/ warnings before we attempt the VM provision. | Keith From Oracle Updated, this is a known issue and some other customer has faced similar problem. Oracle development team is already working on the enhancement request. We have asked for a way to track this for completion
2025-05-02 | ECPU Billing Clarification | Partially Resolved | Medium |  | Enhancement |  |  | ECPU Billing Clarification: We reviewed the document “https://docs.oracle.com/en/learn/scale-ecpu-to-zero/index.html#scale-enabled-ecpus-to-zero” on setting the ECPU to zero to stop billing related to enabled ECPU usage . According to this document, setting the number of ECPUs to zero will eventually shut down the VM cluster. However, we would like to understand why shutting down the VM does not automatically “deallocate” the ECPU. Any additional details on this would be helpful. For now, we will plan to set the ECPU to zero to stop the billing. But will wait for your updates on how we can manage the automatic stop/start VM scripts..Thanks! | Oracle Confirmed the only way to "deallocate" the EPCU is to scale down the VM EPU to Zero and this is the expected behavior. Shutting down the VM will not deallocate the ECPU and the billing will continue. However from fidelity standpoint, this will be operationally challenging as in when the number of VM grows, keeping the last known EPCU configuration of each VM and updating/modifying the scripts to start the VM with the same configuration. Instead if Oracle can automatically deallocate the EPCU/Stop the Billing when we shutdown the VM and start it back with the last known EPCU configuration that will help
| Clarification on DomU OS Patching Frequency + Compatibility Dom0 & DomU | Not Resolved | Medium |  | Enhancement |  |  | We understand that Oracle maintains patching (QFSDP + Monthly Security) on the Dom0 level based on the scheduled maintenance window provided by us. However, we would like to know if we need to maintain the same patch level on the DomU VM clusters to ensure compatibility? In our on-premises Exadata systems, we don't patch the Exadata frequently with quarterly and monthly security patches. Instead, we patch them for major release upgrades or major bug fixes. Performing more frequent patches on the DomU manually adds additional overhead unless we automate the process. Does Oracle provide any automation that we can use to patch the Exadata VM through the OCI Console, or should we manually do it via patchmgr tools? | But from Operation perspective this will be more challenging when we have multiple VM and if we have to scale up and scale down the EPCU depending on the last known configuration
| Shutting down the Database or VM, doesn't reflect the right Status | Not Resolved | Low | 4-0000644424 | Technical Issue |  |  | hen we shut down the database or VM (Scaling the EPCU to 0), the status still reports as available and green for the 'VM Cluster' in the OCI console as well as the AWS side. We would like to understand how this status is being reflected, as our understanding is that when we shut down the VM or database, it should reflect as either down or unavailable. | We had a session with Oracle Cloud OPS team (Tammy) and oracle has confirmed we can defer the DOM0 patching for 180 days and the DOMU can be run in totally a different version than the DOM0 and it won't create any compatibility issues. However Fidelity standard is not to run different versions on Dom0 vs DomU and we want to have the same version on the complete stack. Fidelity would like to take a conservative approach and explore an option of doing the DomU patching in the same maintenance window of DomU. Oracle said the DomU patching can be automated via "Exadata Fleet Update" We have asked oracle(sonali) for a followup Session on this
| On Demand Exachk report Generation Including Dom0 & Storage layer | Not Resolved | Medium |  | Enhancement |  |  | As a customer, we should have the ability to generate a complete ExaCHK report—including both Dom0 and Storage Cells—on demand for our internal review. Currently, this requires opening a service request and waiting for an Oracle SR engineer to provide the report, which introduces delays. This process can be especially problematic during critical incidents when immediate access to the report is essential | Oracle yet to come back with an update
| Rollback patch Option for GI | Not Resolved | Medium |  | Enhancement |  |  | We did a GI Patching through OCI console. But don't see an option to downgrade back to the old Patch Version. However we are able to downgrade the RDBMS to the previous version. Would like to know if similar rollback can be done for GI through the OCI console automation
| OCI Scheduler to Scale the EPCU to 0 | Not Resolved | Low |  | Enhancement |  |  | "Currently, we use a custom script to scale down the ECPU to 0 and shut down the VM. However, we would like to explore the option of scheduling this process using the OCI Resource Scheduler. Relying on a script running externally on an AWS EC2 instance is not ideal, as it becomes unreliable if the EC2 instance becomes unavailable for any reason
| Downgrade Option for GI | Not Resolved | Medium |  | Enhancement |  |  | We did GI and RDBMS upgrade through OCI console. But don't see an option to downgrade back to the old Version. Would like to know if downgrade can be done for GI and RDBMS through the OCI console automation
| Additional patches on Custom Database Home Image | Not Resolved | Medium | 4-0000742778 | Technical Issue |  |  | We have created custome db home images using 2 different approaches - 1) Using opatch lsinv output 2)Passing the additonal patches separately. The custome Image was successfully created but it came with patches in additon to what was passed. We would like to understand more on how Oracle handles custom Image creation and if additonal patches in additon to what was provided is expected.
| Time on the VMs doesn't reflect the correct timezone | Not Resolved | Medium | 4-0000712388 | Technical Issue |  |  | We have observerd that the timezone on the VM servers shows as EST but time that it displays Central time. We would like to know if this is a bug and if this can be updated manually.
| MAA Chaos Testing Service | Not Resolved | Medium |  | Enhancement |  |  | We are looking for a service on OCI to run MAA chaos testing. Something similar to FIS on AWS to simulate chaos scenarios would be helpful.
| Issue with adding standby database from DGMGRL manually | Not Resolved | Medium | 4-0000826469 | Technical Issue |  |  | We have setup the data guard using oci and due to some testing we have removed standby database dg configuration manually. We wanted to know whatour options are to add the standby again. | OPS team was able to fix the issue by synching the config between primary and standby database manually which resolved the issue. Waiting on Vishal to provide the steps for future reference.
| Disable standby database from DGMGRL using console | Not Resolved | Medium |  | Enhancement |  |  | We have setup the data guard using oci and due to some testing we have removed standby database dg configuration manually. Enhancement request to disable/remove DG config temporarily without dropping the DR database. | Enhancement to disable/remove DG config temporarily without dropping the DR database.
| Enable parallel for TDE while using DBAASCLI | Not Resolved | High | Enhancement Request 38916624 | Enhancement |  |  | Enhancement Request 38916624 - NEED PARALLELISM FOR ENCRYPTION WHEN DOING DBAASCLI DATABASE DUPLICATE
| Auto Shutdown/Startup Script for ExaVM (DSDB) | Resolved | [5 empty] | The Script Given By Oracle Keith for Auto Shutdown/Startup of EXA VM is not working as expected, Need the updated Script from Oracle on Handling this along with deallocating the ECPU (Effective Management of Resources for Optimal Billing) |  | DSDB has modified the script to Scale down the ECPU to Zero
2025-05-02 | Event Notifications for Hardware Issues | Resolved | Medium |  | Enhancement |  |  | Event Notifications for Hardware Issues: We did not receive any event notifications once the hardware issues were resolved. Also, the OCI Announcement page does not show these events being cleared. It would be really helpful if we could receive notifications as soon as hardware issues are resolved and be able to track these events in the Health Notification page. |  | Sonali has scheduled a call with Oracle Cloud OPS team for the RCA and they acknowldged the scope of improvement in their current process. From Fidelity Side we want to get notified as soon as theer is a real hardware issue and there should not be any process/communication gap
| Custom Database Image Creation Failure due to "Invalid Inventory Logfile" | Resolved | Low | 4-0000639026 | Technical Issue |  |  | Create Database Software Image operation failed. Failure message: [GICS-1017] [65121] [ocid1.databasesoftwareimage.oc1.iad.anuwcljs53dxrjiaylejdjvzewka5mq27vuo3tf7rkswftotrlravlsdkaha] Unable to get inventory upi from inventory log file b'\n<inventory_upi_response>\n</inventory_upi_response>\n'. Failure cause: Invalid inventory log file format. Suggested action: Check the format and correctness of specified inventory log file. Refer the work request ID 028aac07-aff8-474a-b0da-b3ee12277d68 and GICS job ID 65121 when opening a |  | Able to Create the Gold Image by uploading the opatch lsinventory o/p in the text file format. But this requires manually removing all the special characters in the text file for creating the custom gold image
2025-05-08 | Custom image not getting listed in create database home UI | Partially Resolved | Medium | 4-0000653025 | Technical Issue |  |  | We have created a custom 19.23 RDBMS image, However, in one of the VMs, to create the database home the custom image is not getting listed. |  | We see this Problem intermittently, we will see and open up a new SR if we see the problem again
| Failed Precheck for Quarterly Exadata patching on DOMU | Resolved | High | 4-0000784108 | Technical Issue |  |  | We ran a precheck for Exadata Image patch (25.1.4.0.0.250426) which failed. Looking for Oracle t review the errors from the precheck logs and provide action plan. |  | This was fixed after adding ingress rule with code 8 for ICMP
| Create database failed on orclexavm2 cluster | Resolved | Medium | 4-0000663427 | Technical Issue |  |  | Create Database operation failed. Refer to work request ID 47d2e6e8-eabc-4969-9ac3-2df59527b18e when opening a Service Request at My Oracle Support. [FATAL] [DBAAS-60071] Operation has failed with following error message: [FATAL] ORA-28407: Hardware Security Module failed with PKCS#11 error CKR_FUNCTION_FAILED(6) [FATAL] ORA-28407: Hardware Security Module failed with PKCS#11 error CKR_FUNCTION_FAILED(6) [WARNING] ORA-65017: seed pluggable database may not be dropped or altered.
| TDE KeyStore Type of PDB not matching with database TDE KeyStore Type - KMS | Resolved | High | 4-0000671133 | Technical Issue |  |  | We see the following warning in the Database Home page after the database was created. TDE KeyStore Type of pluggable database(s) - [ORCL3PDB] not matching with database TDE KeyStore Type - KMS. Also the PDB (system and Sysaux) reporting PDB violation with tablespces not encrypted
| Issue with adding standby database from DGMGRL manually | Resolved | Medium | 4-0000826469 | Technical Issue |  |  | We have setup the data guard using oci and due to some testing we have removed standby database dg configuration manually. We wanted to know whatour options are to add the standby again. |  | OPS team was able to fix the issue by synching the config between primary and standby database manually which resolved the issue.
2026-03-03 | Optimizer picked up bad plan despite a fixed sql plan baseline | Resolved |  | 4-0002190867 | Technical Issue |  |  | yesterday one of the critical application API has reported intermittent timeout errors. Upon further investigation we have found that the SQL statement picked up a bad plan despite of SPB. | We have engaged the Oracle support by creating SR # 4-0002190867 and had a call with the engineer. The engineer said that this is not expected behavior and that he has never seen this before. Engineer has confirmed that he has started communication with optimizer team and awaiting their response. In the meantime, Midhun and team has brainstormed some ideas and able to reproduce the issue. Based on our understanding, we suspect that any SQL statement containing TABLE() function is exposed to this behavior and so the plan stability may be at risk even with SPB. We have noticed at least 41 SQL statements matching this pattern, in just one of the critical environments. | Answer yes. - A SQL profile will be applied to the sql-text before parse starts (it basically injects hints). - You could create one manually, to steer the CBO towards using IX3 index, or generate one using coe_gen_sql_profile.sql script (part of SQLT). - An SPM baseline is applied after parse is complete: it validates the outcome of the parse against accepted/enabled plans. - SPM forces an acc/ena plan if parse resulted in something different. - But in that case, in order to do that it first must reproduce the baseline plan (which is where you have hit the bug/issue). The bug to fix the "SPM cannot reproduce plan" issue. - 37682435 (and 39013744): first one is fix, second one is where various backport requests have been made.
2026-03-06 | We need clarification on image version control when creating an Exadata VM Cluster for Oracle Database@AWS through automation. | Not Resolved | sev4 | 4-0002234241 | Enhancement | OCI Compute | vipinkumar galipoina |  |  | Oracle - work in progress Vishal Patil addressed this via call on 3/16 and 3/18 call with Fidelity/Niloy (dev). Follow up in progress
2026-03-05 | Oracle Database@AWS – VM Cluster Stuck in Provisioning State | Resolved | sev3 | 4-0002226132 | Technical Issue | Oracle Cloud Infrastructure - Exadata Cloud Service | vipinkumar galipoina |  |  | Follow up questions adddressed by Oracle Operation via SR. 3/18 call with Oracle Dev/Fidelity also addressed open questions on this SR
2026-03-05 | VCN Flow Logs Not Working | Not Resolved | sev3 | 4-0002225740 | Technical Issue | Oracle Cloud Infrastructure Virtual Networking | James Long |  |  | Oracle - Work in Progress
2026-02-26 | ORA-28353: failed to open wallet | Resolved | sev2 | 4-0002168481 | Technical Issue | Oracle Database@AWS - Exadata Cloud Service | Arijit Talukdar |  |  | (internal team of security who manages IAM, removed a Policy statement then customer was able to bring up DB and issue was fixed. Support working on Follow up questions from Fidelity
2026-02-23 | exachk of DOM0 with all the components | Not Resolved | sev2 | 4-0002134283 | Enhancement | Oracle Database@AWS - Exadata Cloud Service | Mohinder Singh |  |  | Oracle - Work in Progress Oracle internal teams working to determine a slimmed down healthchck report for customer. Danshu will update when ready
2026-02-06 | VM got rebooted - We were doing the Redundancy Testing on interfaces clre0 & stre0, after stopping, the expectations were clre1 & stre1 would pick the connection/traffic. But this didn't happen and both VMs got rebooted. | Resolved | sev2 | 4-0001999344 | Technical Issue | Oracle Database@AWS - Exadata Cloud Service | Mohinder Singh |  |  | 2/12 customer updated issue resolved by using ip link set <interface> down and ip link set <interface> up
2026-02-06 | In Storage server, grid disk is showing as INACTIVE | Resolved | sev2 | 4-0001999148 | Technical Issue | Oracle Database@AWS - Exadata Cloud Service | Mohinder Singh |  |  | 2/18 customer update - Seems "RECOC5 and DATAC5 diskgroup" were associated with "Test POC Cluster" but now its already dropped
2026-01-23 | Customer is trying to duplicate a on-prem database to Oracle@AWS using dbaascli duplicate database - Error Msg - Master key must be set for this container (0) when tablespace_encryption (Hybrid Data Guard encryption) is set | Not Resolved | sev2 | 4-0001868143 | Technical Issue | Oracle Cloud Infrastructure - Exadata Cloud Service | Abhijit Bidar |  |  | No updates from Fidelity - issue resolved? 1/23/26 Support pointed customer to documentation Hybrid DR Data Guard feature with unencrypted on prem primary and mandatory encrypted standby in Oracle Cloud. KB7192 Oracle Database Tablespace Encryption Behavior in Oracle Cloud KB18578
2026-01-20 | DBAASCLI duplication failure | Not Resolved | sev2 | 4-0001840566 | Technical Issue | Oracle Cloud Infrastructure - Exadata Cloud Service | Arijit Talukdar |  |  | ETA for patch April 2026 - Bug 38874772 (AWS: DBAASCLI DUPLICATE DATABASE TIMES OUT AFTER 259200 SECONDS WHILE TABLESPACE ENCRYPTION IN PROGRESS) TBD - ER 38916624 - NEED PARALLELISM FOR ENCRYPTION WHEN DOING DBAASCLI DATABASE DUPLICATE - TBD
2025-12-22 | I am looking patch for the bug - Bug 38485989 - A DELAY OF 6 SECS REPORTED IN REDO SCAN START AFTER. | Resolved | sev3 | 4-0001665284 | Technical Issue | Oracle Database@AWS - Exadata Cloud Service | Kavita Arora |  |  | Confirmed issue closed via email exchanges with Kavita/Anil Nair
2026-02-23 | high "cell single block physical read" waits in ODB@aws | Resolved | sev2 | 4-0002133703 | Technical Issue | Oracle Database@AWS - Exadata Cloud Service | Deepak Vummenthala |  |  | After increasing the SGA size, Fidelity does not see any disk throttling happening or single block physical reads. Zoom scheduled 3/19 to close out any remaining questions
2026-03-05 | Fidelity's Termination of VM cluster completed successfully on the OCI side; however, the resource remained in a Failed state on AWS" | Not Resolved | sev3 | 4-0002227771 | Technical Issue | Oracle Database@AWS - Exadata Cloud Service | Sonali Malik |  |  | AWS/Oracle - work in progress This issue was brought up on 3/18 call with Niloy (dev)

## Q&A
Question Topics | Use Case Clarification | Possible Workaround or Recommendation | Google Documentation Link | Oracle Documentation Link | Responsibility Owner | Next Step | Comment
ODB Network/ ODB Peering Connection/ CIDR Range limit/ NSG Rule limit/ max NSGs in a ODB NW | Each ODB network peering connection can support up to 1024 CIDRs. | As per official Oracle documentation, a single network peering connection can have a limit (often 1024) on the number of CIDR blocks that can be referenced. However, always confirm the latest limits in the OCI Service Limits documentation as these can change |  |  |  | First, we do not support peering up to 1024 CIDRs per ODB Network connection. Regarding NSGs and limits: · An ODB Network can be associated with up to 5 NSGs. · Each NSG supports 120 rules by default. · The rule limit can typically be increased (for example, up to 200 or higher, subject to approval via a service request). · However, attaching multiple NSGs to the ODB Network does not linearly increase the number of CIDRs that can be allowed for database access. To clarify how CIDR allow-listing works for ODB Network peering with Exadata / AVMC: • Security is enforced at the database resource level, not at the ODB Network level. During provisioning, the required security rules are applied directly to the underlying Exadata VM Cluster or AVMC resources. • Peered CIDRs are consolidated into a dedicated security configuration. All CIDRs added through the ODB peering workflow are programmed into a specific NSG/security construct associated with the database resource. • Additional NSGs do not automatically expand CIDR capacity. Only the NSGs explicitly associated with the database resource and used by the service are evaluated for ingress/egress. Creating additional ad-hoc NSGs in the VCN does not increase the number of allowed CIDRs for peering. • The effective limit is driven by security rule limits, not by the number of NSGs. Each CIDR consumes one or more security rules. Therefore, the practical scaling limit is governed by the maximum allowed rules in the relevant NSG. Even if the rule limit is increased via SR, CIDR capacity is still bounded by how rules are consumed. In summary, while you can request rule limit increases, the design does not support scaling to ~1024 CIDRs via NSG expansion.
| We can associate up to 5 NSGs to a ODB Network, and each can support default 120 (or 200 max) rules. | Oracle Cloud Infrastructure (OCI) Network Security Groups (NSGs) have a limit per resource—for many regions/tenancies, the default is 120 rules per NSG, which can sometimes be increased up to 200 via service request. You can associate up to 5 NSGs with a single resource.
| If we attach all 5 NSGs to the ODB network, we should be able to support up to 1000 rules | Associating 5 NSGs (if each has 200 rules max) could allow for a total of up to 1000 rules affecting that resource, assuming all the rules are unique and needed.
| So, we should be able to add up to 1024 CIDR ranges to a ODB Peering connection , until we hit total 1000 NSG rule limit, before we get error. | The CIDR limit (on the peering itself) and NSG rule count are separate limits. The peering connection will enforce its CIDR block limit regardless of your NSGs. Your ability to apply rules to all 1024 CIDRs will depend on your rules' complexity, as you would need one rule per CIDR if treating them all uniquely. The maximum number of rules is enforced per NSG, and the resource limit is on the number of NSGs associated. If you try to create more rules than allowed (by NSG or by association), you will receive an error. Yes, technically, you can have up to 1024 CIDRs in the peering connection and up to 1000 NSG rules (if using 5 NSGs with 200 rules each). However, reaching either limit independently will block further configuration. If you need one NSG rule per CIDR, you’ll hit 1000 before 1024. Additionally, consider the maintainability and performance implications of managing that many NSG rules.
| What NSG limit can we request for our Oracle Database @AWS? We wouldn't want to increase one environment to one value only to learn that we cannot reliably increase our other environments. Can Oracle agree that for Fidelity ODB implementations the NSG limit can be increased to a value higher than 200? If so, what is that value? | We now support 45 peering’s per ODB Network We automatically assign 7 NSGs per ODB Peering Customer can add rules to the ODB peering from AWS Console Standard 120 rules per NSG supports up to 840 (120x7) rules per peering There is a hard limit of 900 rules per peering Hence, we can only increase the rule limit from 120 to 128 within the above construct To accommodate more connections customer should simply add a peering which gives them an additional 840-900 rules The drawback is that they have to manage rules and routing across multiple resources
Fidelity and OCI CloudGuard and DatabaseVault | For CloudGuard, interested in findings across the CSPM, CNAPP (works with exadata?), and Threat. For CSPM, we’d want platform team to remediate this issues and for Threat those are things that probably should go to SOC for investigation and remediation. Looking for details, best practices, and production implementation for notification and remediations… let me know if you need more details. Regarding CloudGuard, we’d be interested in it for general platform security so understood it doesn’t have many specific DB items.. which is where I assume we would use DataSafe in that regards, as you noted - but exadata being managed I am curious what it would show.
Regarding CloudGuard, we’d be interested in it for general platform security so understood it doesn’t have many specific DB items.. which is where I assume we would use DataSafe in that regards, as you noted - but exadata being managed I am curious what it would show.
| We’re trying to find some solutions to the overarching data exfiltration risk and wondering where these tools play in that. | I know we have talked about Data Exfiltration in the past - and we had one of our Database Security PMs give you a sneak preview of Private Service Access (PSA) feature that was forthcoming. (This probably happened around last summer if my memory serves me). This feature has been long awaited and is now generally available. It can potentially be an additional security service for us to investigate with you to utilize for in your security architecture - as it pertains to the Multicloud database. |  | https://blogs.oracle.com/cloud-infrastructure/announcing-private-service-access https://docs.oracle.com/en-us/iaas/exadatacloud/doc/exa-whats-new.html#GUID-1FC1CE33-F064-48C5-A9DE-5E8BBD5A4A47
Do we need the service gateway to allow the ODB offering to function?
What endpoints does the Exadata (or its child resources) need access to?
If we are using Private access and we require the service gateway, can we prevent data exfiltration?Would an alternative be to create a private service access for each service? How would we scale private service access?
Clarify IOPS numbers for X11M Storage Cell Server (High Capacity) ¦¦ODB | running PMA performance testing , understanding IOPS capacity of cell nodes [ X11M Storage Cell Server (High Capacity) ] is critical to map our analysis with respect to 1x/2x loads . Max SQL write IOPS 1,000,000 =1M this 1M including Flash(F) + Disk (H) ?
running PMA performance testing , understanding IOPS capacity of cell nodes [ X11M Storage Cell Server (High Capacity) ] is critical to map our analysis with respect to 1x/2x loads . Max SQL Read IOPS 2,800,000 =2.8M -this 2.8M including Flash + Disk + XRMEM ?
Private Service Access (PSA) to replace Service GW for DB@AWS | Customers can use Private Service Access (PSA) instead of a Service Gateway to provide access to the OCI services required to support the ExaDB-D database service. | A recommended approach would be: Step 1: Identify services currently accessed via the Service Gateway Enable Private DNS logging for the OCI VCN hosting ExaDB-D. Run a full functional test of all customer workflows. Filter the DNS logs for queries routed through the Service Gateway to identify which OCI services are being used. Step 2: Configure PSA for the required OCI services Configure PSA for each identified OCI service (PSA interoperates with OCI Service Gateway). Re-run the full functional test and confirm whether any OCI services are still being accessed through the Service Gateway. If so, configure PSA for those services as well. Step 3: Remove the Service Gateway once PSA coverage is complete After PSA is configured for all required OCI services, delete the Service Gateway from the OCI VCN. Run another full functional test to confirm all features/workflows behave as expected. |  | https://docs.oracle.com/en/engineered-systems/exadata-cloud-service/ecscm/manage-vm-clusters.html#GUID-F30910E0-FA03-414D-8633-D0F2E36C26A0
Can PSA be circumvented via Service Gateway? |  | Yes: a determined actor could route to services via IP and use Service Gateway directly, bypassing DNS-based controls and PSA credential inspection. Why it matters: confirms need for compensating controls and careful coexistence design.
Is OCI Vault supported by PSA today? |  | No; Vault requires continued use of Service Gateway for now. Why it matters: creates a hard dependency that impacts the target-state network pattern.
Does Exadata KMS support cross-region standby? |  | Not currently; only in-region DR. Multi-region support is under development and high priority. Why it matters: affects DR design and encryption/key management strategy for regulated resiliency requirements.
Can Data Safe enrollment be automated during provisioning? |  | Not out-of-the-box; typically day-two. Potential via post-configuration scripting. Why it matters: sets expectations for operational workflow and automation backlog.
How is Data Safe priced for auditing? |  | Included features except activity auditing, which includes up to 1M records/target/month; additional charges per 10K records beyond that. Why it matters: enables cost planning for audit retention and SOC reporting.

## Enablement
On-Site Date | Requester | Follow Up Enablement Topics | Owner | Status | Scheduled Date | Business Units Invloved | Internal SR# | Customer SR#
2026-02-18 | Amardeep | Deep dive ODB@AWS patching
Deep dive hardware failure resolution in ODB, using recent WIDE incident as example
| Jim Long | One pager on ODB escalation flow, contact, phone number
Architecture review on ODB design to ensure it can support tier0/1 workload.
| Sreeni | Review limitations of ODB, ODB peering / CIDR scaling | Julien Siverston/Cataalin Andrei | Complete |  | Brokerage
Capacity planning and management with consolidation
Database migration & cut-over/fail-back approaches (on-prem Exa to Exa@AWS, EC2/VM/RDS to Exa@, non-TDE to Exa@ with TDE
| Abhijit/Jason/Greg | Deep dive on OEM API Ingestion | Alfredo Kreig | open |  | Enterprise | SR0001408064
| Jason | Deep dive on Engineering topics: provisioning & day2 automations using Teraform
| Pratik | Deep dive on AppDBA topics: Goldengate, IORM, TLM, Scaling CPU/Memory
| Vadi | ODB RACI - Oracle/AWS/Fidelity internal teams
| Bala | Tuning, Optimizing for Performance
|  | Federated identity / credentials | Tonmendu | open
|  | India team support / operating model (local resource) | Zahabiya | open
|  | Product feature requests / roadmap timelines | Danshu | Complete | 2026-02-27
|  | Support request (SR) process at scale | Zahabiya | open
|  | Connection Manager | Jibin | Complete | 2/20/2026 (9am) | Brokerage | SR0001411346
|  | Database Vault | Gian | open |  | Brokerage | SR0001408064
|  | Data Safe | Gian | open |  | Brokerage | SR0001408064
|  | CloudGaurd | Tonmendu | Complete | 3/3/2026 (10am) | Enterprise | TBD
|  | Exa IO Breakdown | Chris Kraft/Keith | Compllete | 3/3/2026 (8am) | Brokerage | N/A
|  | Performance and Ops | Rushi | Complete | 2026-02-27 | Brokerage | TBD
|  | Amazon CloudWatch Metrics | palasams@amazon.com | open | 3/4/2026 (2pm) | Brokerage | N/A
|  | Private Service Access (PSA) to replace Service GW for DB@AWS | Lucky | open | 3/5/2026 (3:30pm) | Brokerage | N/A
2026-04-06 |  | Define which CloudGuard detections must route to SOC vs stay within CSPM remediation (e.g., suspicious IP monitoring). | Fran / Security team
|  | Build a service inventory for PSA endpoints using DNS lookup monitoring + VCN flow logs, and maintain Service Gateway for unsupported services. | Chad / Network team
Evaluate/implement controls such as host firewalls, OCI Network Firewall allow lists, packet filtering, and/or endpoint controls (Guardian agent mentioned) to reduce bypass risk.
|  | Provide PSA roadmap timing for OCI Vault support. | Ty
Provide status/trajectory for multi-region Exadata KMS support.
|  | Explore feasible automation approach for Data Safe enrollment during Exadata provisioning (e.g., post-config scripts). | Ty / John